## Roadmap
Epic | Sprint | Objective | Deliverable | Priority | Status | Estimated Effort (h) | Documentation | Definition of Done | Dependencies | Notes
Architecture & Design | S0.1 | Define Project Scope | Project Vision Document | High | Done | 1 | docs/sprints/S0.1.md | Project scope documented
Architecture & Design | S0.2 | Define Folder Structure | Repository Structure | High | Done | 1 | docs/sprints/S0.2.md | Folder structure approved | S0.1
Architecture & Design | S0.3 | Define Naming Standards | Naming Convention Guide | Medium | Done | 1 | docs/sprints/S0.3.md | Naming standards published | S0.2
Architecture & Design | S0.4 | Define Data Models | Data Model Draft | High | Done | 2 | docs/sprints/S0.4.md | Core data models documented | S0.1
Architecture & Design | S0.5 | Define Bronze Silver Gold Strategy | Data Layer Design | High | Done | 2 | docs/sprints/S0.5.md | Medallion architecture documented | S0.2,S0.4
Architecture & Design | S0.6 | Define Physical Data Layout | Catalog / Schema / Dataset Structure | High | Not Started | 1 | docs/sprints/S0.6.md | Physical layout approved | S0.5
Strava Ingestion | S1 | Create Strava Application | Client ID and Client Secret | High | Not Started | 2 | docs/sprints/S1.md | Create Strava Application completed | S0.1
Strava Ingestion | S2 | Implement OAuth Authentication | Refresh Token | High | Not Started | 2 | docs/sprints/S2.md | Implement OAuth Authentication completed | S1
Strava Ingestion | S3 | Extract Athlete Activities | activities.json | High | Not Started | 2 | docs/sprints/S3.md | Extract Athlete Activities completed | S2
Strava Ingestion | S4 | Store Raw Data in Bronze Layer | Organized Raw JSON Files | High | Not Started | 2 | docs/sprints/S4.md | Store Raw Data in Bronze Layer completed | S3,S0.6
Strava Ingestion | S5 | Implement Incremental Loading | state.json | High | Not Started | 2 | docs/sprints/S5.md | Implement Incremental Loading completed | S4
Strava Ingestion | S6 | Add Logging and Error Handling | Execution Logs | Medium | Not Started | 2 | docs/sprints/S6.md | Add Logging and Error Handling completed | S5
Strava Ingestion | S7 | Add Unit Tests | Test Suite | Medium | Not Started | 2 | docs/sprints/S7.md | Add Unit Tests completed | S5
Strava Ingestion | S8 | Improve Project Documentation | Complete README | High | Not Started | 2 | docs/sprints/S8.md | Improve Project Documentation completed | S1-S7
Google Tasks Ingestion | S9 | Create Google Cloud Project | API Credentials | High | Not Started | 2 | docs/sprints/S9.md | Create Google Cloud Project completed | S0.1
Google Tasks Ingestion | S10 | Implement Google Tasks Authentication | OAuth Integration | High | Not Started | 2 | docs/sprints/S10.md | Implement Google Tasks Authentication completed | S9
Google Tasks Ingestion | S11 | Extract Tasks Data | tasks.json | High | Not Started | 2 | docs/sprints/S11.md | Extract Tasks Data completed | S10
Google Tasks Ingestion | S12 | Store Raw Data in Bronze Layer | Organized Raw JSON Files | High | Not Started | 2 | docs/sprints/S12.md | Store Raw Data in Bronze Layer completed | S11,S0.6
Google Tasks Ingestion | S13 | Implement Incremental Loading | state.json | High | Not Started | 2 | docs/sprints/S13.md | Implement Incremental Loading completed | S12
Google Tasks Ingestion | S14 | Add Logging and Tests | Logs and Test Suite | Medium | Not Started | 2 | docs/sprints/S14.md | Add Logging and Tests completed | S13
Silver Layer | S15 | Build Activities Data Model | activities.parquet | High | Not Started | 2 | docs/sprints/S15.md | Build Activities Data Model completed | S4,S0.4
Silver Layer | S16 | Build Exercises Data Model | exercises.parquet | High | Not Started | 2 | docs/sprints/S16.md | Build Exercises Data Model completed | S12,S0.4
Silver Layer | S17 | Add Data Quality Checks | Validation Framework | Medium | Not Started | 2 | docs/sprints/S17.md | Add Data Quality Checks completed | S15,S16
Silver Layer | S18 | Add Technical Metrics | Data Profiling Report | Low | Not Started | 2 | docs/sprints/S18.md | Add Technical Metrics completed | S17
Gold Layer | S19 | Build Weekly Summary Dataset | weekly_summary | High | Not Started | 2 | docs/sprints/S19.md | Build Weekly Summary Dataset completed | S15,S16
Gold Layer | S20 | Build Monthly Summary Dataset | monthly_summary | High | Not Started | 2 | docs/sprints/S20.md | Build Monthly Summary Dataset completed | S19
Gold Layer | S21 | Build Personal Records Dataset | personal_records | High | Not Started | 2 | docs/sprints/S21.md | Build Personal Records Dataset completed | S15
Gold Layer | S22 | Build Training Streaks Dataset | streaks | Medium | Not Started | 2 | docs/sprints/S22.md | Build Training Streaks Dataset completed | S19
Gold Layer | S23 | Build Training Score Dataset | training_score | Medium | Not Started | 2 | docs/sprints/S23.md | Build Training Score Dataset completed | S19
Analytics | S24 | Create Streamlit MVP | Initial Dashboard | High | Not Started | 2 | docs/sprints/S24.md | Create Streamlit MVP completed | S19-S23
Analytics | S25 | Build KPI Dashboard | KPI Overview Page | High | Not Started | 2 | docs/sprints/S25.md | Build KPI Dashboard completed | S24
Analytics | S26 | Add Trends Analysis | Weekly and Monthly Trends | Medium | Not Started | 2 | docs/sprints/S26.md | Add Trends Analysis completed | S25
Analytics | S27 | Implement Goal Tracking | Goal Tracking Dashboard | Medium | Not Started | 2 | docs/sprints/S27.md | Implement Goal Tracking completed | S25
Analytics | S28 | Add Interactive Filters | Filterable Dashboard | Low | Not Started | 2 | docs/sprints/S28.md | Add Interactive Filters completed | S25
API | S29 | Create FastAPI Application | Running API Service | Medium | Not Started | 2 | docs/sprints/S29.md | Create FastAPI Application completed | S19-S23
API | S30 | Create Activities Endpoint | GET /activities | Medium | Not Started | 2 | docs/sprints/S30.md | Create Activities Endpoint completed | S29
API | S31 | Create Statistics Endpoint | GET /stats | Medium | Not Started | 2 | docs/sprints/S31.md | Create Statistics Endpoint completed | S29
API | S32 | Create Records Endpoint | GET /records | Low | Not Started | 2 | docs/sprints/S32.md | Create Records Endpoint completed | S29
DevOps | S33 | Dockerize Application | Dockerfile | Low | Not Started | 2 | docs/sprints/S33.md | Dockerize Application completed | S24,S29
DevOps | S34 | Create GitHub Actions CI Pipeline | CI Workflow | Medium | Not Started | 2 | docs/sprints/S34.md | Create GitHub Actions CI Pipeline completed | S33
DevOps | S35 | Automate Data Refresh | Scheduled Execution | Low | Not Started | 2 | docs/sprints/S35.md | Automate Data Refresh completed | S34
DevOps | S36 | Add Code Quality Checks | Linting and Formatting | Medium | Not Started | 2 | docs/sprints/S36.md | Add Code Quality Checks completed | S34
Advanced Analytics | S37 | Correlate Cardio and Strength Training | Correlation Analysis | Medium | Not Started | 2 | docs/sprints/S37.md | Correlate Cardio and Strength Training completed | S23
Advanced Analytics | S38 | Build Fitness Consistency Metrics | Consistency Dataset | Medium | Not Started | 2 | docs/sprints/S38.md | Build Fitness Consistency Metrics completed | S22
Advanced Analytics | S39 | Analyze Performance Trends | Trend Analysis Report | Medium | Not Started | 2 | docs/sprints/S39.md | Analyze Performance Trends completed | S37,S38
Advanced Analytics | S40 | Generate AI-Based Insights | AI Insights Engine | Low | Not Started | 2 | docs/sprints/S40.md | Generate AI-Based Insights completed | S39
Cloud & Data Engineering Extensions | S41 | Store Data in Azure Data Lake | ADLS Integration | Low | Not Started | 2 | docs/sprints/S41.md | Store Data in Azure Data Lake completed | S15-S23
Cloud & Data Engineering Extensions | S42 | Process Data with Databricks | Databricks Pipeline | Low | Not Started | 2 | docs/sprints/S42.md | Process Data with Databricks completed | S41
Cloud & Data Engineering Extensions | S43 | Implement Delta Tables | Delta Lake Layer | Low | Not Started | 2 | docs/sprints/S43.md | Implement Delta Tables completed | S42
Cloud & Data Engineering Extensions | S44 | Introduce Data Cataloging | Metadata Layer | Low | Not Started | 2 | docs/sprints/S44.md | Introduce Data Cataloging completed | S43
Cloud & Data Engineering Extensions | S45 | Build End-to-End Cloud Architecture | Cloud Deployment | Low | Not Started | 2 | docs/sprints/S45.md | Build End-to-End Cloud Architecture completed | S44

## Future Backlog
Future Idea | Description
Garmin Integration | Import Garmin activities
Fitbit Integration | Health and activity data
Google Calendar Integration | Calendar correlation
Weight Tracking | Body weight history
Nutrition Tracking | Nutrition metrics
Power BI Reporting | Business reporting
Unity Catalog | Data governance
Lakehouse Monitoring | Observability
Machine Learning Models | Predictive analytics
Training Recommendation Engine | Personalized recommendations
Weather Correlation Analysis | Weather impact analysis
Race Preparation Metrics | Competition readiness

## Sprint Details Template
Sprint | Description | Acceptance Criteria | Definition of Done | Documentation | Dependencies

## Architecture Decisions
Decision ID | Date | Topic | Decision | Rationale
ADR-001 |  | Physical Data Layout | Use folder-based catalog/schema simulation | Simple local lakehouse approach